## Gantt Chart
PROJECT: Formula SAE Electric Vehicle (IN PROGRESS, WILL UPDATE WITH INDIVIDUAL TASKS WHEN ASSIGNED)
Tennesssee Tech University |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Evan Morse, Jesse Munoz, Erlind Boraj, Zach Holt, Graham Robinson
Project start date: | 2024-09-01 |  |  |  |  | September | [34 empty] | October
Scrolling increment: | 0 | time axis 2024-09-01 to 2024-10-26
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-09-01 to 2024-10-26
Project development
Team Contract | Milestone | Erlind Boraj | 100% | 2024-09-01 | 3 | bar: 2024-09-01 to 2024-09-03
Proposal Draft | On Track | All Members | 100% | 2024-09-04 | 7
Proposal Final Submission | On Track | All Members | 100% | 2024-09-11 | 20
Conceptual Design | Med Risk | All Members | 20% | 2024-09-28 | 30
Detailed Design | Med Risk | All Members | 0% | 2024-10-28 | 34
Design/Building
Begin Building Project | Med Risk |  | 0% | 2025-01-20 | 82
Project Scope Finished, Testing and Fixing Issues | High Risk |  | 0% | 2025-04-11 | 21
To add more data, Insert new rows ABOVE this one